## Slide 1
Proposal · YSD-2026-AVF
Issued 29 August 2026 · Valid to 12 September 2026
PREPARED FOR AV FARM SUPPLIES
Landing page,
content, and
leads in 30 days.
One page that converts, your existing content pushed out organically and behind paid spend, and every enquiry landing somewhere you can act on it.
TOTAL — FIXED
JMD $40,000
YardScale Digital · yardscaledigital@gmail.com
Notes: Cover. Fixed price of JMD $40,000 for a 30-day engagement: landing page, organic and paid distribution of existing content, and lead generation.

## Slide 2
THE SHORT VERSION
02
What you get, in a paragraph
Your landing page is built. Over the next thirty days we put it to work: your existing photos and video reformatted and posted on a schedule that holds, paid campaigns behind the pieces that perform, and every lead that comes back captured in one place with a name, a number and what they asked about. At day 30 you get the numbers and a written next step — and you can carry on month to month.
CLIENT
AV Farm Supplies
ENGAGEMENT
30 days
TOTAL
JMD $40,000
DEPOSIT
JMD $20,000
BY DAY 30 YOU HAVE
A landing page you own outright, documented and handed over
Thirty days of posting and paid spend, managed end to end
A written report on leads, cost per lead and what to do next
Notes: Summary slide. Emphasise: fixed price, no surprise billing, and that day 30 ends with real numbers rather than a renewal conversation in the dark.

## Slide 3
WHAT'S INCLUDED
03
The page, and the posting
WEB
The landing page, live and yours
One page with one job — turn a visit into an enquiry
Mobile-first, built to load fast on local mobile data
Enquiry form plus click-to-chat into your WhatsApp
Products, prices and delivery areas laid out plainly
Hosting configured, domain connected, analytics wired in
Handed over documented — nothing you run depends on us
ORGANIC
Your content, posted properly
Built from content you already have — product shots, yard photos, video
Reformatted, captioned and cut for each platform
A posting calendar built and run by us for the full 30 days
Hooks and angles tested against each other, not guessed at
What performs gets made again; what doesn’t gets dropped
Notes: Scope part one. The page is the destination; organic is the free traffic feeding it from content they already own — no new shoot required.

## Slide 4
WHAT'S INCLUDED
04
The spend, and the leads
PAID
Advertising behind what works
Meta campaigns — Facebook and Instagram — built and managed
Audiences targeted by parish, farming type and buying intent
Ad creative cut from your existing content, not stock
Monitored daily, budget moved to the ads that convert
Retargeting for people who hit the page and didn’t enquire
LEADS
Lead generation and handover
Every enquiry captured in one place — shared sheet or your inbox
Name, contact, source, and what they were asking about
Reply templates so nothing sits unanswered overnight
Weekly check-in on what’s coming in and what it costs
Day-30 report: leads, cost per lead, best content, next step
Ad spend is paid by AV Farm Supplies directly to Meta and sits outside this quote. You set the daily budget and you keep control of it.
Notes: Scope part two. Be explicit about ad spend being separate and client-controlled — this is the single most common misunderstanding on a paid engagement.

## Slide 5
TIMELINE
05
The thirty days
1
WEEK 1
Set up
Page finalised and tracking installed. Ad accounts, pixel and channels prepared. Existing content audited and sorted into what we can use.
2
WEEK 2
Live
Landing page goes live. The organic calendar starts posting. First paid campaigns launch with the strongest creative we have.
3
WEEK 3
Read and adjust
Two weeks of real numbers. Losing ads switched off, budget moved behind winners, fresh hooks cut from what week 2 told us.
4
WEEK 4
Push and report
The angles that work get scaled to month end. You get the day-30 report and a written recommendation for what comes next.
Ends with a deliverable, not a renewal call. Day 30 is a written report — leads in, cost per lead, best-performing content — and a recommendation you can act on with or without us.
Notes: Timeline. Week 2 is the launch milestone and it is also when the balance falls due — worth saying out loud.

## Slide 6
INVESTMENT
06
One fixed price
ITEM
INCLUDED
Landing page
Build, launch, hosting setup and documented handover
Organic content distribution — 30 days
Reformatting, captions, calendar built and managed
Paid advertising — 30 days
Campaign build, creative, daily management and optimisation
Lead generation and reporting
Capture system, reply templates, weekly check-ins, day-30 report
TOTAL — FIXED
JMD $40,000
PAYMENT 1 — TO START
50%
JMD $20,000
Due on acceptance. Work begins the day it clears.
PAYMENT 2 — ON LAUNCH
50%
JMD $20,000
Due the day the page is live and campaigns are running.
Nothing is billed on top of this figure, and it does not change once the deposit is paid.
Notes: Money slide. JMD $40,000 total. 50% (JMD $20,000) on acceptance, 50% (JMD $20,000) on launch. Ad spend is separate and paid direct to Meta.

## Slide 7
SCOPE AND INPUTS
07
Where the edges are
NOT IN THIS QUOTE
×
Ad spend — paid direct to Meta by you
×
New photo or video shoots
×
Online checkout or card payments
×
Print, radio or outdoor advertising
×
Work past day 30 — that’s the retainer
WHAT WE NEED FROM YOU
01
Existing content — product photos and video
02
Product list, prices and the areas you deliver to
03
Logo files and anything brand-related you have
04
Admin access to Facebook and Instagram
05
The WhatsApp number enquiries should reach
06
One person who can answer questions and sign off
07
A daily ad budget you’re comfortable with
Everything on the right is content and access you already own. None of it costs you anything extra — it just needs to reach us in week 1 so the timeline holds.
Notes: Boundaries slide. Say plainly that late access in week 1 is the one thing that moves the timeline.

## Slide 8
AFTER DAY 30
Carry on, month to month
The thirty days stand on their own. At the end of it the page is yours, the content system is documented, and you have real numbers on what a lead costs you. Nothing in this proposal locks you into anything after that.
What continues
Posting calendar, paid campaign management, lead handling and a monthly report — the same engine, kept running.
How it’s priced
The retainer rate is set at the day-30 review, against what the first month actually produced. You never pay against a guess.
How it ends
Month to month, thirty days’ notice either way. No lock-in, no minimum term, no exit fee.
TO ACCEPT
Sign the proposal and send the deposit of JMD $20,000. Week 1 starts the day it clears.
yardscaledigital@gmail.com
Notes: Close. The retainer is genuinely optional and priced off month-one data. Ask for the signature and the deposit before leaving the call.